## Sheet1
Project Name | Sections | Completed (out of 100%) | Completed modules | Pending modules | Why Pending
1.GreytHr | Self login / Employee login | 90% | -->All most all | -->Functionality wise completed. -->due to lack of resourse for testing, not able give a 100%
| Hr/Admin | 20% | -->onboarding -->Employee Information -->grant leaves | (more to know about Hr side functionality) | Need to get inputs from HR admin side
| IT | Basic(10%) | -->Asset details | -->in progress | Need to get inputs from IT admin side
| Pay roll | Not yet started | Not yet | Not yet | on Hold
2.IT snow | Catalog, Assets | in Progress(80%) | in progress | Need to be tested | need inputs for further implementation
3.Marzii | UI | completed(90%) | UI Done | -->no pending
| Backend | completed with setup(20%) | database and tables completed | -->pending with payment related setup
| Implementaion | Starting level(20%) -->currently in progress | -->login & register(done) -->adding vendors(done) | -->payment check out implementaion -->Neee data to be added
4.CMS | Upto Date as per the requirement | Upto Date as per the requirement | -->customers,vendors,Employee,Contractor Registrations -->SOPO, Bills and invoices | -->time sheet pending as per manohar sir requirement | Upto Date
5.Ankapur Chicken | Desktop(Python) | 70% | -->getting ankapur menu list | -->SMS service, Reports -->need to integrate Swiggy&Zomato -->Product management(admin side) | Need to purchase SMS services
| Mobile(Flutter & backend laravel) | 70% | -->getting ankapur menu list | -->SMS service, Reports -->need to integrate Swiggy&Zomato
6.Recon | Upto Date as per the requirement | Upto Date as per the requirement | Upto Date as per the requirement | Upto Date as per the requirement